PROJECT COST BREAKDOWN

Dental AI Detection System — OPG Analysis & Implant Assessment

| Prepared by: EbusinessPal Sdn. Bhd. ML & Software Development | Prepared for: Clavis Labs / Ghaith Hafez Date: 23 June 2026 |
| --- | --- |

## Executive Summary

This document outlines the full cost breakdown for the Dental AI Detection System — a three-stage machine learning pipeline that analyses panoramic dental X-rays (OPGs) and generates preliminary implant treatment plans for call center staff. Pricing reflects the technical complexity of the work, market rates for medical AI development, and the full scope of deliverables as defined in the Detection Specification Brief.

All rates are in USD. For NGN or MYR conversion, apply the agreed exchange rate at contract signing. Final invoice will be in the agreed currency.

## What Is Included

- Full ML pipeline: Stage 1 (tooth detection), Stage 2A (pathology classification), Stage 2B (landmark regression)

- DENTEX dataset preprocessing, CLAHE enhancement, COCO → YOLO conversion

- Auto-resume training system — safe against PC shutdowns and interruptions

- Clinical rules engine: sinus lift and nerve proximity assessment with hardcoded thresholds

- End-to-end inference pipeline: OPG image → structured JSON report

- Call center UI: interactive FDI tooth chart with color-coded severity flags

- Technical documentation, deployment packaging, and client handover session

## What Is Not Included (Separate Scope)

- Landmark annotation of sinus floor and nerve canal (requires client-provided annotated OPGs — min. 200 images)

- CBCT integration (3D bone volume analysis — requires separate scoping)

- Clinical validation by a licensed dental radiologist

- Cloud compute costs (billed at cost if training is moved to cloud)

- Ongoing model retraining after delivery

## Detailed Cost Breakdown

| Phase 1 — Data Engineering & Preprocessing |  |  |  |
| --- | --- | --- | --- |
| Deliverable | Hours | Rate (USD/hr) | Amount (USD) |
| Dataset audit & structure validation | 4 hrs | $55 | $220 |
| DICOM/PNG pipeline + CLAHE preprocessing | 6 hrs | $55 | $330 |
| COCO → YOLO label conversion | 5 hrs | $55 | $275 |
| Train/val/test split + dataset YAML | 3 hrs | $55 | $165 |
| Phase Subtotal |  |  | $990 |

| Phase 2 — Stage 1: Tooth Detection (YOLOv8-seg) |  |  |  |
| --- | --- | --- | --- |
| Deliverable | Hours | Rate (USD/hr) | Amount (USD) |
| YOLOv8-seg architecture setup & config | 5 hrs | $65 | $325 |
| FDI 32-class segmentation training | 12 hrs | $65 | $780 |
| Missing tooth gap detection logic | 4 hrs | $65 | $260 |
| Model evaluation (mAP@0.5, mAP@0.5-0.95) | 4 hrs | $65 | $260 |
| Checkpoint + auto-resume system | 3 hrs | $65 | $195 |
| Phase Subtotal |  |  | $1,820 |

| Phase 3 — Stage 2A: Pathology Classifier (EfficientNet-B3) |  |  |  |
| --- | --- | --- | --- |
| Deliverable | Hours | Rate (USD/hr) | Amount (USD) |
| EfficientNet-B3 model + custom head | 5 hrs | $65 | $325 |
| Per-tooth crop extraction pipeline | 4 hrs | $65 | $260 |
| Multi-class training: caries, periapical, crown, RCT | 10 hrs | $65 | $650 |
| Class imbalance handling + weighted loss | 3 hrs | $65 | $195 |
| AUC-ROC evaluation per disease class | 3 hrs | $65 | $195 |
| Phase Subtotal |  |  | $1,625 |

| Phase 4 — Stage 2B: Landmark Regression (U-Net) |  |  |  |
| --- | --- | --- | --- |
| Deliverable | Hours | Rate (USD/hr) | Amount (USD) |
| U-Net architecture + regression head | 8 hrs | $70 | $560 |
| Gaussian heatmap generation pipeline | 4 hrs | $70 | $280 |
| Sinus floor + nerve canal training | 10 hrs | $70 | $700 |
| MRE (mean radial error) evaluation in mm | 3 hrs | $70 | $210 |
| Annotation specification for client data | 2 hrs | $70 | $140 |
| Phase Subtotal |  |  | $1,890 |

Note: Stage 2B billing begins when client delivers annotated landmark data (min. 200 OPGs)

| Phase 5 — Clinical Rules Engine |  |  |  |
| --- | --- | --- | --- |
| Deliverable | Hours | Rate (USD/hr) | Amount (USD) |
| Sinus lift threshold logic (CLEAR / CAUTION / LIFT) | 4 hrs | $60 | $240 |
| Nerve proximity threshold logic (CLEAR / RISK) | 4 hrs | $60 | $240 |
| Implant site report generator (per missing tooth) | 4 hrs | $60 | $240 |
| Bone height → mm conversion calibration | 2 hrs | $60 | $120 |
| Phase Subtotal |  |  | $840 |

| Phase 6 — Inference Pipeline & Integration |  |  |  |
| --- | --- | --- | --- |
| Deliverable | Hours | Rate (USD/hr) | Amount (USD) |
| End-to-end OPG → JSON report pipeline | 6 hrs | $65 | $390 |
| Stage 1 → 2A → 2B orchestration | 5 hrs | $65 | $325 |
| DICOM + PNG + JPG input handling | 3 hrs | $65 | $195 |
| Structured JSON report schema | 3 hrs | $65 | $195 |
| Phase Subtotal |  |  | $1,105 |

| Phase 7 — Call Center UI |  |  |  |
| --- | --- | --- | --- |
| Deliverable | Hours | Rate (USD/hr) | Amount (USD) |
| Interactive FDI tooth chart (color-coded) | 8 hrs | $70 | $560 |
| CLEAR / CAUTION / RISK flag display | 4 hrs | $70 | $280 |
| Per-tooth findings panel | 5 hrs | $70 | $350 |
| Report export (PDF / print) | 3 hrs | $70 | $210 |
| Phase Subtotal |  |  | $1,400 |

| Phase 8 — Project Management & Delivery |  |  |  |
| --- | --- | --- | --- |
| Deliverable | Hours | Rate (USD/hr) | Amount (USD) |
| Technical documentation & README | 4 hrs | $55 | $220 |
| Deployment packaging + environment setup | 4 hrs | $55 | $220 |
| Client walkthrough & handover session | 3 hrs | $55 | $165 |
| Bug fixes & revisions (post-delivery) | 5 hrs | $55 | $275 |
| Phase Subtotal |  |  | $880 |

## Cost Summary

| Phase | Description | Subtotal (USD) |
| --- | --- | --- |
| Phase 1 | Data Engineering & Preprocessing | $990 |
| Phase 2 | Stage 1 — Tooth Detection (YOLOv8-seg) | $1,820 |
| Phase 3 | Stage 2A — Pathology Classifier | $1,625 |
| Phase 4 | Stage 2B — Landmark Regression (U-Net) | $1,890 |
| Phase 5 | Clinical Rules Engine | $840 |
| Phase 6 | Inference Pipeline & Integration | $1,105 |
| Phase 7 | Call Center UI | $1,400 |
| Phase 8 | Project Management & Delivery | $880 |
| — | Contingency Reserve (10%) | $1,155 |
| TOTAL PROJECT COST |  | $11,705 |

A 10% contingency reserve ($1,155) is included to cover scope edge cases, extra revision rounds, and unforeseen technical challenges. If unused, this amount is either refunded or applied to future work at the client's discretion.

## Payment Schedule

| Milestone | Deliverable | % Due | Amount (USD) |
| --- | --- | --- | --- |
| Milestone 1 | Project kickoff & contract signing | 30% | $3,512 |
| Milestone 2 | Preprocessing + Stage 1 model delivered | 25% | $2,926 |
| Milestone 3 | Stage 2A + clinical rules engine delivered | 25% | $2,926 |
| Milestone 4 | Full pipeline + UI + Stage 2B (if data ready) | 20% | $2,341 |

All milestone payments are due within 7 days of delivery and acceptance. Stage 2B (landmark regression) payment is triggered upon receipt of client-annotated landmark data, not upon contract signing.

## Optional Add-ons

| Add-on | Notes | Estimate (USD) |
| --- | --- | --- |
| Cloud training (Colab Pro / vast.ai) | Billed at cost + 10% mgmt fee | ~$150–300 |
| CBCT integration (3D bone volume) | Scope to be defined | ~$3,000–4,500 |
| Dental radiologist clinical audit (50 OPGs) | External cost, passed through | ~$500–800 |
| Ongoing model maintenance (per month) | Bug fixes + retraining support | $400/mo |
| Additional annotation (per 100 OPGs) | Via Scale AI or Label Studio | ~$1,500–2,500 |

## Terms & Conditions

- Quote is valid for 30 days from the date of issue.

- Rates are fixed for the agreed scope. Out-of-scope changes are quoted separately before work begins.

- Source code and trained model weights are transferred to the client upon final payment.

- Client is responsible for ensuring all patient X-rays used for training comply with applicable privacy regulations (HIPAA, PDPA, or equivalent).

- A clinical disclaimer will be embedded in every AI-generated report: findings require confirmation by a licensed dentist.

- Intellectual property developed during this project is exclusively owned by the client upon full payment.

EbusinessPal Sdn. Bhd.  |  Medical AI Development

This document is confidential and intended solely for the named recipient.